## Read Me
Questbase — Role-Based QA Test Plan
Generated 2026-09-10 against main @ becc167. Production: https://www.questbase.io
How to use
1. Work one role sheet at a time, signed in as that role. Do not test two roles in one session.
2. Put an x in Done, then set Status. Use Notes for the actual behaviour when it differs.
3. A test that cannot run yet is Blocked, not Fail — say why in Notes.
4. Access Control & Negative is the sheet that matters most. Every case there is a 'must not', and
several must be checked against the API directly, not only the screen. A hidden button is not a gate.
Roles under test — taken from src/main.js, not invented
owner / admin / developer Elevated. Permission '*'. Inherit every active child workspace automatically.
manager 35 permissions. Broad operational access, no user/role/billing/settings admin.
member 12 permissions. Task-capable, mostly read elsewhere.
member with NO role 5 permissions only: jobs.view, tasks.view, users.view, settings.view, plugins.view.
Important: the ROLE_PERMISSIONS table in src/main.js is the DEMO/LOCAL fallback only.
A live Supabase session reads role_permissions from the database. Test against a live session —
if the two ever disagree, the database wins and the UI is wrong.
Environments
Production https://www.questbase.io Do not run destructive cases here.
Local npm run dev -> 127.0.0.1:5173 Requires npm ci first.
Sheets
Permission Matrix Role x permission reference, generated from the code.
Admin QA Owner / admin / developer.
Manager QA Includes explicit boundary cases the manager must NOT pass.
Member QA Includes the no-role default set.
Access Control & Negative Tenant isolation, RLS, privilege escalation, public surfaces.
Cross-Cutting Auth, routing, data integrity, mobile, a11y, performance, build.

## Permission Matrix
Permission | owner / admin / developer | manager | member | member (no role)
jobs.view | YES | YES | YES | YES
jobs.manage | YES | YES | — | —
tasks.view | YES | YES | YES | YES
tasks.manage | YES | YES | YES | —
files.view | YES | YES | YES | —
files.manage | YES | YES | — | —
forms.view | YES | YES | YES | —
forms.manage | YES | YES | — | —
workspaces.view | YES | YES | — | —
workspaces.manage | YES | YES | — | —
workspaces.settings.manage | YES | — | — | —
workspaces.records.view | YES | — | — | —
workspaces.records.create | YES | — | — | —
workspaces.records.edit | YES | — | — | —
workspaces.records.delete | YES | — | — | —
workspaces.records.export | YES | — | — | —
workspaces.records.import | YES | — | — | —
client_portals.view | YES | YES | — | —
client_portals.manage | YES | YES | — | —
crm.view | YES | YES | — | —
crm.manage | YES | YES | — | —
company_contacts.view | YES | — | — | —
company_contacts.create | YES | — | — | —
company_contacts.edit | YES | — | — | —
company_contacts.delete | YES | — | — | —
company_contacts.fields.manage | YES | — | — | —
company_contacts.manage | YES | — | — | —
underwriter.view | YES | YES | — | —
underwriter.manage | YES | YES | — | —
finance.view | YES | YES | — | —
finance.manage | YES | — | — | —
users.view | YES | YES | YES | YES
team.view | YES | YES | — | —
users.manage | YES | — | — | —
roles.view | YES | YES | — | —
roles.manage | YES | — | — | —
plugins.view | YES | — | — | YES
plugins.manage | YES | — | — | —
billing.view | YES | YES | — | —
billing.manage | YES | — | — | —
settings.view | YES | YES | — | YES
settings.manage | YES | — | — | —
time.track | YES | — | YES | —
clock.manage | YES | YES | — | —
approvals.view | YES | YES | YES | —
approvals.manage | YES | YES | — | —
calendar.view | YES | YES | YES | —
calendar.manage | YES | YES | — | —
calendar.view_team | YES | YES | — | —
messages.view | YES | YES | YES | —
messages.send | YES | YES | YES | —
messages.create_group | YES | YES | — | —
messages.manage_groups | YES | YES | — | —
messages.attach_files | YES | YES | YES | —
messages.delete_own | YES | — | — | —
messages.delete_any | YES | — | — | —
messages.manage | YES | — | — | —
eod.view | YES | — | — | —
eod.manage | YES | — | — | —
price_book.view | YES | YES | — | —
price_book.manage | YES | YES | — | —

## Admin QA
Done | Test ID | Role | Module / Area | Category | Test Case | Steps | Expected Result | Priority | Status | Notes
| ADM-001 | Admin | Access | Functional | Elevated role reaches every module | Sign in as owner/admin/developer. Visit each of the 21 module routes under /company/<slug>/… | All 21 load. Elevated roles are '*' in ROLE_PERMISSIONS and inherit every active child workspace. | High | Not Run
| ADM-002 | Admin | Access | Functional | Admin inherits workspaces without explicit membership | As admin, open /company/<slug>/workspaces without adding yourself to any workspace | Every active child workspace is listed and openable; no workspace_memberships row is required. | High | Not Run
| ADM-003 | Admin | Users & Access | Functional | Invite a new user | People & Access > Invite. Enter email, pick role, send | Invite created, pending state shown, email dispatched, invite is unique per pending email. | High | Not Run
| ADM-004 | Admin | Users & Access | Functional | Re-invite the same email while one is pending | Invite the same address twice | Second attempt is refused or replaces the first; no duplicate pending invite rows. | High | Not Run
| ADM-005 | Admin | Users & Access | Functional | Change a member's role | People & Access > pick member > change role > save | Role saves; the member's permissions change on their next load; audit records the change. | High | Not Run
| ADM-006 | Admin | Users & Access | Functional | Suspend and restore a member | Suspend an active member, then restore | Suspended member loses access immediately; restore returns prior access; data untouched. | High | Not Run
| ADM-007 | Admin | Users & Access | Functional | Remove a member from the company | People & Access > Remove member > confirm | Membership revoked; the person's authored records remain and show their name. | High | Not Run
| ADM-008 | Admin | Users & Access | Security | Owner cannot be demoted by a non-owner | As admin (not owner), try to change the primary owner's role | Refused. Primary owner protection holds; no privilege escalation path. | High | Not Run
| ADM-009 | Admin | Roles | Functional | Create a custom role | Roles > New role > name it > tick permissions > save | Role persists with exactly the ticked keys; the picker shows all 61 permission keys. | High | Not Run
| ADM-010 | Admin | Roles | Functional | team.view is grantable from the Roles editor | Roles > edit a role > find 'View team chart' | The checkbox exists and, when granted, unlocks /company/<slug>/team-chart for that role. | High | Not Run
| ADM-011 | Admin | Roles | Functional | Delete a role that is in use | Assign a role to someone, then delete the role | Either blocked with a clear message, or members fall back to the default read-only set — never a crash. | High | Not Run
| ADM-012 | Admin | Roles | Security | Granular contact keys behave independently | Create a role with company_contacts.create only. Sign in as it. | Can file a contact; cannot edit, delete, or reach field/card-layout management. | High | Not Run
| ADM-013 | Admin | Roles | Security | Legacy company_contacts.manage still satisfies the split keys | Create a role with only company_contacts.manage | All four granular powers work (alias behaviour) — pre-split roles keep working unchanged. | High | Not Run
| ADM-014 | Admin | Workspaces | Functional | Create an operational workspace | Workspaces > Create. Name, icon, colour, description, members | Workspace created, appears in the sidebar rail, opens its own setup questionnaire. | High | Not Run
| ADM-015 | Admin | Workspaces | Functional | Rename needs workspaces.settings.manage, not settings.manage | Grant only workspaces.settings.manage to a role; rename a workspace as that role | Rename succeeds without granting company settings (brand, modules, integrations, launch). | High | Not Run
| ADM-016 | Admin | Workspaces | Functional | Archive and restore a workspace | Archive a non-default workspace, confirm it leaves the rail, restore it | Archive hides it and preserves data; the default workspace cannot be archived. | High | Not Run
| ADM-017 | Admin | Workspaces | Functional | Set the default workspace | Mark another workspace as default | Exactly one default per company; the old default is cleared atomically. | High | Not Run
| ADM-018 | Admin | Workspaces | Functional | Reorder the sidebar rail | Drag workspaces into a new order; reload | Order persists per company and survives reload. | High | Not Run
| ADM-019 | Admin | Workspaces | Functional | Delete a workspace | Delete a workspace with apps and records; confirm | Removal is atomic; sibling workspaces and company records are untouched. | High | Not Run
| ADM-020 | Admin | App Builder | Functional | Create an app with every field type | Workspace > New app. Add text, textarea, number, category, status, date, checkbox, file, image, relationship, calculation, button, user, url, duration | Every field type renders in the record form and list, and saves its value. | High | Not Run
| ADM-021 | Admin | App Builder | Functional | Calculation field evaluates | Add a calculation referencing two number fields; create a record | Result computes live and matches the evaluator; referencing another calculation does not silently read 0. | High | Not Run
| ADM-022 | Admin | App Builder | Functional | Relationship field links records | Add a relationship to another app; pick a linked record | Link saves, displays the target's title, and opens the target record. | High | Not Run
| ADM-023 | Admin | App Builder | Functional | Automations fire | Create an automation (trigger + action); satisfy the trigger | Action runs once, and the activity log records it with the automation's name. | High | Not Run
| ADM-024 | Admin | App Builder | Functional | Saved views persist per app | Create a filtered/sorted view; reload | View persists, is selectable, and does not leak to other apps. | High | Not Run
| ADM-025 | Admin | App Builder | Functional | Child collections (sub-item lists) | Declare a sub-item list on an app; add rows inside a record | Sub-items save against the record and do not appear as app-level fields. | High | Not Run
| ADM-026 | Admin | Import / Export | Functional | Export records to CSV | Open an app > Export | CSV downloads with one column per field, and a row appears in the Import & Export tab. | High | Not Run
| ADM-027 | Admin | Import / Export | Functional | Download app as .questapp.json | Open an app > Download app | Bundle downloads carrying fields, automations and items; a transfer row is recorded. | High | Not Run
| ADM-028 | Admin | Import / Export | Functional | Import a CSV | Import a CSV whose headers match some fields, some not | Matched columns import; unmatched and un-importable columns are named, not just counted. | High | Not Run
| ADM-029 | Admin | Import / Export | Functional | Imported records carry provenance | Import a CSV, open one of the new records, view its activity | Record activity shows 'Imported from <filename>' — not 'Nothing yet'. | High | Not Run
| ADM-030 | Admin | Import / Export | Functional | Import is not logged twice | Import a CSV and open the workspace feed | The import appears once, from the transfer log — not duplicated by a workspace activity line. | High | Not Run
| ADM-031 | Admin | Import / Export | Functional | Print counts as an export | Open an app > Print | A transfer row of format 'print' is recorded; Print is gated on workspaces.records.export. | High | Not Run
| ADM-032 | Admin | Clear Log | Functional | Clear log removes activity AND import/export rows | Configure workspace > Clear log > re-auth > confirm. Then open the workspace feed and an app's Import & Export tab | Activity entries and export/import rows are both gone. This is the 2026-09-09 fix; previously the transfer lines survived. | High | Not Run
| ADM-033 | Admin | Clear Log | Functional | Clearing leaves a tombstone per app | After clearing, open the Import & Export tab of each app that had rows | Each shows a 'Cleared — N entries — <who> — <when>' line, not an empty 'Nothing has moved yet' table. | High | Not Run
| ADM-034 | Admin | Clear Log | Security | Clearing twice leaves two tombstones | Clear, create an export, clear again. Inspect the Import & Export tab | Both tombstones remain. The DELETE policy excludes direction='cleared', so evidence of a clear cannot be erased. | High | Not Run
| ADM-035 | Admin | Clear Log | Functional | Clear log states the counts before you agree | Open the Clear log confirm dialog | It names the number of logged actions and the number of import & export entries that will go. | High | Not Run
| ADM-036 | Admin | Clear Log | Security | Clear log requires re-authentication | Trigger Clear log on a live session | Password is requested and verified before anything is cleared; a wrong password clears nothing. | High | Not Run
| ADM-037 | Admin | Clear Log | Security | A refused clear clears nothing at all | Simulate a database refusal during the clear (e.g. revoke the role mid-flight) | An error is shown and the activity log still has its entries — no half-cleared state. | High | Not Run
| ADM-038 | Admin | Clear Log | Security | Clear log never touches the feed or audit trail | Post to the workspace feed, upload a file, then clear the log | Posts and files remain; company audit_events are untouched. | High | Not Run
| ADM-039 | Admin | Recycle Bin | Functional | Delete and restore a record | Delete an app record, open Recycle bin, restore it | Record returns with its values and its history intact. | High | Not Run
| ADM-040 | Admin | Recycle Bin | Functional | Permanent delete | Recycle bin > permanently delete an item | Item is gone and does not return after reload; the action is recorded. | High | Not Run
| ADM-041 | Admin | Recycle Bin | Data | Contact field deletion has no recycle bin | Delete a company-contact field definition | The UI warns that this is unrecoverable before proceeding. | High | Not Run
| ADM-042 | Admin | Company Contacts | Functional | Add, edit, delete a contact | Company Contacts > add, edit, delete | Each operation is gated by its own granular permission key and persists. | High | Not Run
| ADM-043 | Admin | Company Contacts | Functional | Field and card layout management | Add a field, rearrange the contact card layout | Layout persists per company and renders on every contact. | High | Not Run
| ADM-044 | Admin | Company Contacts | Functional | Bulk select and bulk actions | Select several contacts, apply a bulk action | Action applies to exactly the selected rows; the count shown matches. | High | Not Run
| ADM-045 | Admin | Company Contacts | Functional | Contact merge is one transaction | Merge duplicate contacts | Every reference moves; the duplicate is only recycled if the merge returns cleanly. | High | Not Run
| ADM-046 | Admin | Settings | Functional | Company brand and appearance | Setup > brand: change name, logo, colours, theme | Changes persist, sync across devices, and apply to the shell without a hard reload. | High | Not Run
| ADM-047 | Admin | Settings | Functional | Enable and disable a module | Setup > modules: disable a module, reload, re-enable | Disabling hides the module and preserves its data; re-enabling restores access. | High | Not Run
| ADM-048 | Admin | Settings | Functional | Pipeline stage editing | Setup > pipelines: rename, add, reorder, delete stages | Existing records are re-pointed via the rename map; no record is orphaned. | High | Not Run
| ADM-049 | Admin | Settings | Functional | Guided workspace setup apply and reset | Run the questionnaire, apply the plan, then reset | Apply is atomic and idempotent; reset clears only that workspace's answers and draft, not applied config. | High | Not Run
| ADM-050 | Admin | Billing | Functional | View and manage subscription | Admin > billing | Current plan and state are shown; checkout session opens for an upgrade. | High | Not Run
| ADM-051 | Admin | Plugins | Functional | Install and disable a plugin | Plugins > install, then disable | Entitlement is per company; disabling preserves data; workspace activation is separate. | High | Not Run
| ADM-052 | Admin | Files | Functional | Upload, preview, download, delete | Files > upload a PDF, an image, an Office doc; preview each; delete one | All upload within policy limits, preview correctly, and delete cleanly. | High | Not Run
| ADM-053 | Admin | Files | Security | Upload policy rejects disallowed types | Attempt to upload a file type outside the allowed list | Rejected client-side and server-side with a clear message. | High | Not Run
| ADM-054 | Admin | Forms | Functional | Build and publish a form | Forms > build with several question types > publish | Public link works; only published question types/options are accepted on submit. | High | Not Run
| ADM-055 | Admin | Forms | Functional | Form file upload binds to one response | Submit a public form with a file attached | Upload intent is claimed atomically with the response; a reused or expired intent is rejected. | High | Not Run
| ADM-056 | Admin | Forms | Functional | Delete a form response | Open a response and delete it | Response is removed; attached storage objects are handled per policy. | High | Not Run
| ADM-057 | Admin | Client Portals | Functional | Create and share a portal | Client Portals > create > share link | Portal opens for the recipient via a scoped token, not broad tenant access. | High | Not Run
| ADM-058 | Admin | Finance | Functional | Create and edit finance records | Finance > create an entry, edit it | Persists; finance attachments land in the hardened bucket. | High | Not Run
| ADM-059 | Admin | Price Book | Functional | Manage vendors, materials, costs, import | Price Book > add vendor, add material, set cost, import a catalogue | All persist; import reports matched and skipped rows. | High | Not Run
| ADM-060 | Admin | Reports | Functional | Analytics and dashboards render | Open /company/<slug>/analytics and dashboard widgets | Widgets render with real counts; empty states are explicit, not blank. | High | Not Run
| ADM-061 | Admin | Audit | Security | Audit trail records privileged actions | Perform a role change, a member removal and a workspace delete; open the audit view | All three appear with actor, target and timestamp; entries cannot be edited or deleted from the UI. | High | Not Run
| ADM-062 | Admin | Backups | Functional | Workspace backup create and list | Create a workspace backup; list backups | Backup is created and listed with metadata only; restricted to settings managers. | High | Not Run
| ADM-063 | Admin | Platform Panel | Security | Platform master panel is platform-admin only | Sign in as a normal company admin and attempt to open the platform panel | Refused. Only is_platform_admin() accounts reach it. | High | Not Run
| ADM-064 | Admin | Time & Approvals | Functional | Clock dashboard and approvals queue | Open /company/<slug>/clock and /approvals | Entries list, approve/reject works, and data-quality problems are visible rather than silently rewritten. | High | Not Run
| ADM-065 | Admin | EOD | Functional | Review anyone's EOD report | With eod.manage, open another person's EOD report and edit it | Report opens and saves; without eod.manage only your own is reachable. | High | Not Run

## Manager QA
Done | Test ID | Role | Module / Area | Category | Test Case | Steps | Expected Result | Priority | Status | Notes
| MGR-001 | Manager | Access | Functional | Manager reaches its granted modules | Sign in as manager. Open jobs, tasks, files, forms, crm, underwriter, finance, calendar, messages, client-portals, workspaces, team-chart | All load. These map to the manager permission set. | High | Not Run
| MGR-002 | Manager | Jobs | Functional | Create, edit and stage a job | Jobs > create > edit fields > move stage | Saves; stage change is recorded in record history with the actor. | High | Not Run
| MGR-003 | Manager | Jobs | Functional | Bulk delete jobs | Select several jobs and delete | Only selected jobs are removed; the count matches; deletions are recoverable per policy. | High | Not Run
| MGR-004 | Manager | Jobs | Functional | Job photos and voice notes | Attach photos and a voice note to a job | Both upload, display in the job record, and survive reload. | High | Not Run
| MGR-005 | Manager | Jobs | Functional | Change orders | Run the change-order wizard on a job | Line items save and totals recalculate. | High | Not Run
| MGR-006 | Manager | CRM | Functional | Create a contact and move it through stages | CRM > new contact > advance stage | Stage change logs an activity entry and updates 'What's next'. | High | Not Run
| MGR-007 | Manager | CRM | Functional | Delete a CRM record (crm.manage) | Delete a contact as manager | Allowed — crm.manage is the delete key and manager holds it. | High | Not Run
| MGR-008 | Manager | CRM | Functional | Contact to quote graduation | Convert a contact into a quote/deal | Atomic; the quote carries the contact and account references. | High | Not Run
| MGR-009 | Manager | Tasks | Functional | Create, assign, complete a task | Tasks > create > assign to a teammate > complete | Assignment notifies; completion updates the linked record's 'What's next'. | High | Not Run
| MGR-010 | Manager | Tasks | Functional | Task recurrence | Create a recurring task; complete one occurrence | Next occurrence is generated on the correct date. | High | Not Run
| MGR-011 | Manager | Tasks | Data | Task conflict merge | Edit the same task in two tabs; save both | Only locally changed fields reapply; unrelated concurrent changes survive; same-field conflict favours the current editor. | High | Not Run
| MGR-012 | Manager | Files | Functional | Upload and delete files (files.manage) | Upload a file, then delete it | Both allowed for manager. | High | Not Run
| MGR-013 | Manager | Forms | Functional | Create and edit forms (forms.manage) | Create a form, edit its questions | Allowed and persists. | High | Not Run
| MGR-014 | Manager | Underwriter | Functional | Takeoff and calculator | Open Underwriter, run a takeoff, use the calculator | Values compute and save to the case. | High | Not Run
| MGR-015 | Manager | Finance | Read-only | Finance is view-only for manager | Open Finance as manager and attempt to create or edit an entry | Records are visible (finance.view) but create/edit controls are absent or refused — manager lacks finance.manage. | High | Not Run
| MGR-016 | Manager | Price Book | Functional | Manage the price book | Add a vendor and a material; adjust costs | Allowed — manager holds price_book.manage. | High | Not Run
| MGR-017 | Manager | Calendar | Functional | Create events and view the team calendar | Create an event; switch to team view | Both allowed — manager holds calendar.manage and calendar.view_team. | High | Not Run
| MGR-018 | Manager | Messages | Functional | Create and manage group chats | Create a group, add members, rename it, attach a file | Allowed — manager holds messages.create_group, manage_groups and attach_files. | High | Not Run
| MGR-019 | Manager | Messages | Functional | Leave and clear a conversation | Leave a group; clear a conversation | Leaving removes you only; clearing affects your view per the documented semantics. | High | Not Run
| MGR-020 | Manager | Client Portals | Functional | Create and edit a client portal | Create a portal and edit its content | Allowed — manager holds client_portals.manage. | High | Not Run
| MGR-021 | Manager | Workspaces | Functional | Build workspace apps (workspaces.manage) | Create an app, add fields, add an automation | Allowed for manager. | High | Not Run
| MGR-022 | Manager | Approvals | Functional | Approve and reject | Open Approvals, approve one item and reject another | Both persist and notify the requester. | High | Not Run
| MGR-023 | Manager | Clock | Functional | Manage the clock dashboard | Open the clock dashboard, correct an entry | Allowed — manager holds clock.manage; corrections are visible as corrections. | High | Not Run
| MGR-024 | Manager | Team | Functional | Team chart and workload | Open team-chart and team workload | Both render — manager holds team.view. | High | Not Run
| MGR-025 | Manager | Boundary | Security | Manager cannot invite or manage users | Open People & Access as manager | Members are visible (users.view) but Invite / role-change / remove controls are absent and refused server-side. Manager lacks users.manage. | High | Not Run
| MGR-026 | Manager | Boundary | Security | Manager cannot create or edit roles | Attempt to open the Roles editor as manager | Read-only at most (roles.view); no create/edit. Manager lacks roles.manage. | High | Not Run
| MGR-027 | Manager | Boundary | Security | Manager cannot manage billing | Open billing as manager | Plan is visible (billing.view) but no subscription changes. Manager lacks billing.manage. | High | Not Run
| MGR-028 | Manager | Boundary | Security | Manager cannot manage company settings | Attempt brand/modules/integrations changes as manager | Refused. Manager holds settings.view only. | High | Not Run
| MGR-029 | Manager | Boundary | Security | Manager cannot install or disable plugins | Attempt a plugin change as manager | Refused — manager holds neither plugins.manage nor plugins.view by default. | High | Not Run
| MGR-030 | Manager | Boundary | Security | Manager cannot export app records unless granted | As manager, open an app and look for Export / Print / Download app | Absent unless workspaces.records.export is explicitly granted — it is not in the manager set. | High | Not Run

## Member QA
Done | Test ID | Role | Module / Area | Category | Test Case | Steps | Expected Result | Priority | Status | Notes
| MBR-001 | Member | Access | Functional | Member sees only assigned workspaces | Sign in as a member assigned to one workspace of several | Only the assigned workspace appears. Regular workers need explicit workspace_memberships. | High | Not Run
| MBR-002 | Member | Access | Functional | Member can hold a different role per workspace | Assign the same person different roles in two workspaces | Each workspace applies its own role; permissions do not bleed across. | High | Not Run
| MBR-003 | Member | Jobs | Read-only | Jobs are view-only | Open Jobs as member; attempt to create or edit | List and detail render (jobs.view); create/edit controls absent and refused. Member lacks jobs.manage. | High | Not Run
| MBR-004 | Member | Tasks | Functional | Member can create and edit tasks | Create a task, edit it, complete it | Allowed — member holds tasks.manage. | High | Not Run
| MBR-005 | Member | Files | Read-only | Files are view-only | Open Files; attempt upload and delete | Files are viewable; upload/delete absent and refused. Member lacks files.manage. | High | Not Run
| MBR-006 | Member | Forms | Read-only | Forms are view-only | Open Forms; attempt to edit a form | Viewable only. Member lacks forms.manage. | High | Not Run
| MBR-007 | Member | Time | Functional | Member tracks own time | Clock in, clock out, review own entries | Own entries save. time.track is own-time only — the clock dashboard needs clock.manage. | High | Not Run
| MBR-008 | Member | Approvals | Read-only | Member views approvals but cannot decide | Open Approvals; attempt to approve | Queue is visible (approvals.view); approve/reject refused. Member lacks approvals.manage. | High | Not Run
| MBR-009 | Member | Calendar | Read-only | Member views the calendar | Open Calendar; attempt to create an event | View works; create refused. Member lacks calendar.manage and calendar.view_team. | High | Not Run
| MBR-010 | Member | Messages | Functional | Member sends messages and attaches files | Send a direct message with an attachment | Allowed — member holds messages.send and messages.attach_files. | High | Not Run
| MBR-011 | Member | Messages | Security | Member cannot create or manage group chats | Attempt to create a group chat as member | Refused. Member lacks messages.create_group and messages.manage_groups. | High | Not Run
| MBR-012 | Member | Users | Read-only | Member sees the directory but cannot change it | Open People & Access as member | Directory visible (users.view); no invite, role change, or removal. | High | Not Run
| MBR-013 | Member | CRM | Security | Member has no CRM access by default | Attempt /company/<slug>/crm as member | Refused or empty-with-explanation. Member holds neither crm.view nor crm.manage. | High | Not Run
| MBR-014 | Member | Finance | Security | Member has no finance access | Attempt /company/<slug>/finance as member | Refused. Member holds neither finance.view nor finance.manage. | High | Not Run
| MBR-015 | Member | Workspaces | Security | Member cannot build workspace apps | Attempt to add a field or app as member | Refused. Member lacks workspaces.manage. | High | Not Run
| MBR-016 | Member | No-role | Security | Active member with NO role gets the minimal set | Add someone to the company without assigning a role | Exactly jobs.view, tasks.view, users.view, settings.view, plugins.view — and nothing more. | High | Not Run
| MBR-017 | Member | No-role | Security | No-role member cannot reach records | As a no-role member, attempt an app record list | Refused. workspaces.records.view is not in the default set. | High | Not Run

## Access Control & Negative
Done | Test ID | Role | Module / Area | Category | Test Case | Steps | Expected Result | Priority | Status | Notes
| NEG-001 | All | Tenant Isolation | Security | No cross-company data via the UI | Sign in to company A; try to open a company B record URL directly | Refused. RLS scopes every read to current_company_ids(). | Critical | Not Run
| NEG-002 | All | Tenant Isolation | Security | No cross-company data via the API | With company A's session token, query a company B row through PostgREST | Zero rows. Verified by the rollback-only tenant probe, not just the UI. | Critical | Not Run
| NEG-003 | All | Tenant Isolation | Security | Cross-workspace record isolation | As a member of workspace 1, request a workspace 2 record id | Refused. has_workspace_permission gates by workspace membership. | Critical | Not Run
| NEG-004 | All | Permissions | Security | Paint matches the gate | For each hidden control, call the underlying endpoint directly | The server refuses independently. A hidden button must never be the only protection. | Critical | Not Run
| NEG-005 | All | Permissions | Security | Export cannot be reached without the export key | Remove workspaces.records.export from a role; call the export path directly | Refused. Export, Print and Download app all gate on the same key. | Critical | Not Run
| NEG-006 | All | Permissions | Security | Import cannot be reached without the import key | Remove workspaces.records.import; attempt an import | Refused server-side, not merely hidden. | Critical | Not Run
| NEG-007 | All | Transfer Log | Security | The transfer log cannot be edited | Attempt an UPDATE on wb_data_transfers as an authenticated user | Refused. There is no UPDATE policy and UPDATE is revoked (2026-09-09). | Critical | Not Run
| NEG-008 | All | Transfer Log | Security | The transfer log cannot be truncated | Attempt TRUNCATE on wb_data_transfers as authenticated | Refused. TRUNCATE bypasses RLS, so the grant itself was revoked (2026-09-09). | Critical | Not Run
| NEG-009 | All | Transfer Log | Security | Only workspaces.manage may clear transfers | As a role without workspaces.manage, attempt to delete transfer rows | Refused by the 'wb transfers clear' policy. | Critical | Not Run
| NEG-010 | All | Transfer Log | Security | Tombstones survive a delete-everything attempt | As a manager, issue a blanket delete of the workspace's transfer rows | Export/import rows go; direction='cleared' rows remain, because USING excludes them. | Critical | Not Run
| NEG-011 | All | Privilege Escalation | Security | A manager cannot grant themselves more | As manager, attempt to edit your own role's permissions | Refused — roles.manage is required and manager does not hold it. | Critical | Not Run
| NEG-012 | All | Privilege Escalation | Security | Self-elevation to owner is impossible | Attempt to set your own membership role to owner via the API | Refused by the self-privilege-escalation guard. | Critical | Not Run
| NEG-013 | All | Public Surfaces | Security | Public form submit is service-role only | Call submit_public_form_response as an authenticated (non-service) user | Raises 'service role required'. | Critical | Not Run
| NEG-014 | All | Public Surfaces | Security | Fabricated upload paths are rejected | Submit a public form referencing a storage path you invented | Rejected. The endpoint verifies the real Storage object, size and type. | Critical | Not Run
| NEG-015 | All | Public Surfaces | Security | Expired or reused upload intents are rejected | Reuse a claimed intent, and use one past its 30-minute expiry | Both rejected; the response is not created. | Critical | Not Run
| NEG-016 | All | Public Surfaces | Security | Public demo stays read-only | Open the public demo and attempt any write | All writes refused; bundled sample data is unchanged. | Critical | Not Run
| NEG-017 | All | Public Surfaces | Security | Client portal tokens are narrowly scoped | Take a portal link and try to reach unrelated company data with it | Refused. Portals use scoped server APIs, not broad tenant access. | Critical | Not Run
| NEG-018 | All | Auth | Security | No account enumeration | Sign in with an unknown email and with a wrong password | Both give the same non-revealing error. | Critical | Not Run
| NEG-019 | All | Auth | Security | Suspended member is locked out immediately | Suspend a member with an active session; have them act | Next request is refused; a stale token does not keep working. | Critical | Not Run
| NEG-020 | All | Auth | Security | Rate limits hold | Repeat sign-in and public form submits past the configured limit | Durable per-IP and per-form limits engage and reset correctly. | Critical | Not Run
| NEG-021 | All | Headers | Security | Security headers present in production | curl -I https://www.questbase.io | CSP enforced with script-src 'self', HSTS, COOP, nosniff, X-Frame-Options, Referrer-Policy, Permissions-Policy. | Critical | Not Run
| NEG-022 | All | Headers | Security | CSP blocks eval and inline script | Attempt an inline script and an eval in the console context | Blocked by the enforced policy; violations report to /api/csp-report. | Critical | Not Run

## Cross-Cutting
Done | Test ID | Role | Module / Area | Category | Test Case | Steps | Expected Result | Priority | Status | Notes
| XC-001 | All | Auth | Functional | Sign up, verify, sign in, sign out | Complete the full registration flow end to end | Each step works and lands on the right screen. | High | Not Run
| XC-002 | All | Auth | Functional | Password reset, including an expired link | Request a reset; use the link; then reuse the expired link | Reset works once; the expired link fails with a clear message. | High | Not Run
| XC-003 | All | Auth | Functional | OAuth invite join | Accept a company invite using an OAuth provider | Account links to the invite and membership is created once. | High | Not Run
| XC-004 | All | Routing | Functional | Deep links survive a cold load | Paste a deep record URL into a new tab while signed out | Sign-in is requested, then the original destination opens — not the dashboard. | High | Not Run
| XC-005 | All | Routing | Functional | Legacy .html routes redirect | Open /crm.html, /finance.html, /messages.html | Each redirects to the modern route with the redirect marker. | Medium | Not Run
| XC-006 | All | Routing | Functional | Unknown route | Open /company/<slug>/does-not-exist | A clear not-found state, not a blank screen or endless spinner. | Medium | Not Run
| XC-007 | All | Errors | Functional | A failed lazy module shows Try again | Throttle the network so a route chunk fails | The skeleton is replaced by a visible Try again state, not an endless placeholder. | High | Not Run
| XC-008 | All | Errors | Functional | Settings load failure degrades | Force the settings query to fail | An explicit error with a retry, not a half-rendered page. | Medium | Not Run
| XC-009 | All | Data | Data | Draft recovery for interrupted typing | Start a Contact/Job/Quote/Underwriter form, reload mid-typing | The same-browser draft is offered; it never becomes shared company data on its own. | High | Not Run
| XC-010 | All | Data | Data | Record history records who changed what | Change whitelisted fields on a Contact, Quote, Job and Task | History shows actor, field and time, and preserves delete/restore within workspace permissions. | High | Not Run
| XC-011 | All | Data | Data | Optimistic save failures do not lie | Force a save to fail (offline, or revoke permission mid-edit) | The UI reports the failure and does not show the change as saved. | High | Not Run
| XC-012 | All | Data | Data | Paging beyond the API row cap | Load a record directory with more rows than the PostgREST cap | Full list pages with stable ordering; recent-activity feeds stay intentionally bounded. | Medium | Not Run
| XC-013 | All | Realtime | Functional | Live updates across two sessions | Open the same record in two browsers; change it in one | The other updates without a manual refresh. | Medium | Not Run
| XC-014 | All | Realtime | Functional | Presence and live users | Have two people open the same surface | Presence reflects both, and clears on disconnect. | Low | Not Run
| XC-015 | All | Tasks Embed | Functional | Embedded Tasks keeps its iframe | Trigger host re-renders while the embedded Tasks surface is open mid-interaction | The iframe is not reparented; scroll, session and unfinished input survive. | High | Not Run
| XC-016 | All | Mobile | Responsive | Core flows on a phone viewport | At 390x844 run sign-in, dashboard, a record open, and a save | No horizontal scroll; controls reachable; density rules apply. | High | Not Run
| XC-017 | All | Mobile | Responsive | Sidebar and rail on small screens | Collapse/expand the sidebar on mobile and tablet | Toggle works, does not trap focus, and remembers state. | Medium | Not Run
| XC-018 | All | Accessibility | Accessibility | Keyboard-only navigation | Tab through sign-in, a dialog and a record form | Focus order is sensible, focus is visible, and dialogs trap focus correctly. | High | Not Run
| XC-019 | All | Accessibility | Accessibility | Dialogs own the keyboard | Open a modal while the command palette is available | The dialog receives keystrokes; the palette does not intercept or linger behind it. | High | Not Run
| XC-020 | All | Accessibility | Accessibility | Colour contrast | Check text and controls in light and dark themes | Meets contrast thresholds in both, including sidebar themes. | Medium | Not Run
| XC-021 | All | Accessibility | Accessibility | Screen reader labels | Traverse icon-only buttons with a screen reader | Every control has an accessible name. | Medium | Not Run
| XC-022 | All | Performance | Performance | Entry bundle stays within budget | Run npm run build | Bundle budget passes; entry JS is under the enforced ceiling. | High | Not Run
| XC-023 | All | Performance | Performance | First paint on a cold load | Hard-reload the dashboard with cache disabled | Two-phase boot renders the shell quickly; heavy modules load on demand. | Medium | Not Run
| XC-024 | All | Performance | Performance | Large workspace app stays usable | Open an app with a few thousand records; scroll, filter, sort | No lock-ups; scroll position is preserved across renders. | Medium | Not Run
| XC-025 | All | Cross-Browser | Compatibility | Chrome, Edge, Firefox, Safari | Run sign-in, a record edit and a file upload in each | Consistent behaviour and layout. | High | Not Run
| XC-026 | All | Cross-Browser | Compatibility | iOS Safari and Android Chrome | Run the same three flows on real devices | Consistent; file pickers and date inputs behave. | Medium | Not Run
| XC-027 | All | Build | Technical | Full check gate passes | npm run check | Tests, project-brain check, tenancy matrix, build and bundle budget all pass. | High | Not Run
| XC-028 | All | Build | Technical | Production smoke with the commit pinned | npm run smoke:prod -- --base-url https://www.questbase.io --expect-sha <sha> | 36/36 routes pass with 4/4 entry assets and the deployed commit matches. | High | Not Run
| XC-029 | All | Build | Technical | Snapshot freshness gate | Add a migration without refreshing .ai/database/snapshot.json | npm run tenancy:check refuses to certify; it must not pass over a stale snapshot. | High | Not Run
| XC-030 | All | Content | UX | Empty states explain themselves | Visit each module with no data | Each says what will appear and how to create the first item. | Medium | Not Run
| XC-031 | All | Content | UX | Destructive actions state their scope | Open every destructive confirm dialog | Each names what will be removed, what is kept, and whether it can be undone. | High | Not Run